## Sheet1
Task | Responsible | Time (EST) | What: Prod Cutover to RCM Cloud environment (Classic)
Turn off Insight interfaces / background services | Medsphere | 22:30
Disable nightly processes and Waystar tasks | Medsphere | 22:40 | When: Tuesday, June 16th - Wendesday, June 17th
Disable Insight users | Medsphere | 22:50
Ensure users are off the system | Medsphere | 23:00 | Prerequisites | Responsible
Take databases offline??? | Medsphere | 23:10 | All RCM users should have previously accessed RCM Portal, and confirmed ability to login to Classic (aat-rcm) | AAT
Backup databases (Ics_Ashley & Sislnk) | Medsphere | 23:20 | User(s) confirmed ability to scan via Classic cloud | AAT
Begin image copy from on-prem to cloud | Medsphere | 23:25 | User(s) tested auto printing of journals to ensure it works in the cloud | AAT
Restore databases in Cloud (to aat-rcm & aat-sislnk) | Medsphere | 24:00 | Reporting Services reports copied to cloud and functional | Medsphere
Upgrade databases to 2019.3 & miscellaenous scripts | Medsphere | 25:00 | Tier->Insurance Verification interface configured and tested | Medsphere/AAT
Enable users in Insight Cloud | Medsphere | 25:20
Turn on Insight interfaces / background services | Medsphere | 25:50
Repoint Sequest interfaces to cloud (port 7501) | AAT | ????
Verification of SQL Jobs | Medsphere | 26:20
Verification of nightly jobs/billing | Medsphere | 2:30
Verification of Waystar tasks | Medsphere | 2:50
Install Tier->Ins Verification bat configuration | AAT | ????
AAT Users login | AAT | 7:00
Support | AAT/Medsphere