## Sheet1
Project: RCM Server: https://dev.azure.com/medsphere Query: SMG Tag Work Items Tree List type: Tree
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Assigned To | State | Effort | Original Estimate | Remaining Work | Area Path | Iteration Path | Tags
3292 | Epic | Sana Medical Group |  |  |  | Patrick Lim | New | 55 |  |  | \DevOps\core.srvcs | \RCM Services\2020\20Q3 | HL7; LeadTools; MCSP; RCM; SMG; SQL; SSL; SSRS
3293 | Feature |  | SMG Provision at MCSP |  |  | Patrick Lim | New | 34 |  |  | \DevOps\tenant.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; LeadTools; MCSP; RCM; SMG
3294 | Product Backlog Item |  |  | Deploy Web Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; MCSP; RCM; SMG; SSL
3298 | Task |  |  |  | Install LeadTools Service | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; MCSP; SMG; SSL
3299 | Task |  |  |  | Install RCM Webapp Sites | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; RCM; SMG; SSL
3305 | Task |  |  |  | Install SignalR Sites | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG; SSL
3317 | Task |  |  |  | Configure Kerberos for Web Services | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG
3318 | Task |  |  |  | Install Maintenance Sites | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG
3319 | Task |  |  |  | Notify Support Team of All Resources | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3320 | Task |  |  |  | Publish to Parallels Portal | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3295 | Product Backlog Item |  |  | Deploy App Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; MCSP; RCM; SMG; SSL
3300 | Task |  |  |  | Set Up Folder Structures and Shares | Patrick Lim | To Do |  | 1 | 1 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; RCM; SMG
3301 | Task |  |  |  | Configure Interface Services | Patrick Lim | To Do |  | 2 | 2 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; RCM; SMG
3302 | Task |  |  |  | Install InsightCS and ODBCs | Patrick Lim | To Do |  | 2 | 2 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3315 | Task |  |  |  | Configure Scheduled Tasks | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3316 | Task |  |  |  | Install SSMS on App Server | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3321 | Task |  |  |  | Set Up Ipswitch or Similar FTP Tool | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
3296 | Product Backlog Item |  |  | Deploy Data Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | MCSP; RCM; SMG; SQL; SSL; SSRS
3303 | Task |  |  |  | Restore Model DBs | Patrick Lim | To Do |  | 2 | 2 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG; SQL; SSAS; SSL; SSRS
3304 | Task |  |  |  | Install Power BI Report Server | Patrick Lim | To Do |  | 2 | 2 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; RCM; SMG; SQL; SSL; SSRS
3306 | Task |  |  |  | Configure Replication | Patrick Lim | To Do |  | 3 | 3 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; SMG; SQL; SSL; SSRS
3308 | Task |  |  |  | Set Up Domain and Insight Logins | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
3309 | Task |  |  |  | Configure Maintenance Plan | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
3310 | Task |  |  |  | Configure Kerberos for Data Services | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
3311 | Task |  |  |  | Update Data Paths | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
3312 | Task |  |  |  | SMG Install RDL Files for Reporting | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; SMG; SQL; SSRS
3313 | Task |  |  |  | Install Analysis Server | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
3314 | Task |  |  |  | Configure Agent Jobs | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL

## Sheet3
Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Assigned To | State | Effort | Original Estimate | Remaining Work | Area Path | Iteration Path | Tags
Epic | Sana Medical Group |  |  |  | Patrick Lim | New | 55 |  |  | \DevOps\core.srvcs | \RCM Services\2020\20Q3 | HL7; LeadTools; MCSP; RCM; SMG; SQL; SSL; SSRS
Feature |  | SMG Provision at MCSP |  |  | Patrick Lim | New | 34 |  |  | \DevOps\tenant.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; LeadTools; MCSP; RCM; SMG
Product Backlog Item |  |  | Deploy Web Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; MCSP; RCM; SMG; SSL
Task |  |  |  | Install LeadTools Service | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; MCSP; SMG; SSL
Task |  |  |  | Install RCM Webapp Sites | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; LeadTools; RCM; SMG; SSL
Task |  |  |  | Install SignalR Sites | Patrick Lim | To Do |  | 2 | 2 | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG; SSL
Task |  |  |  | Configure Kerberos for Web Services | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG
Task |  |  |  | Install Maintenance Sites | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | IIS; SMG
Task |  |  |  | Notify Support Team of All Resources | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Task |  |  |  | Publish to Parallels Portal | Patrick Lim | To Do |  |  |  | \DevOps\web.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Product Backlog Item |  |  | Deploy App Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; MCSP; RCM; SMG; SSL
Task |  |  |  | Set Up Folder Structures and Shares | Patrick Lim | To Do |  | 1 | 1 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; RCM; SMG
Task |  |  |  | Configure Interface Services | Patrick Lim | To Do |  | 2 | 2 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | HL7; RCM; SMG
Task |  |  |  | Install InsightCS and ODBCs | Patrick Lim | To Do |  | 2 | 2 | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Task |  |  |  | Configure Scheduled Tasks | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Task |  |  |  | Install SSMS on App Server | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Task |  |  |  | Set Up Ipswitch or Similar FTP Tool | Patrick Lim | To Do |  |  |  | \DevOps\app.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG
Product Backlog Item |  |  | Deploy Data Services |  | Patrick Lim | Approved | 8 |  |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | MCSP; RCM; SMG; SQL; SSL; SSRS
Task |  |  |  | Restore Model DBs | Patrick Lim | To Do |  | 2 | 2 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | RCM; SMG; SQL; SSAS; SSL; SSRS
Task |  |  |  | Install Power BI Report Server | Patrick Lim | To Do |  | 2 | 2 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; RCM; SMG; SQL; SSL; SSRS
Task |  |  |  | Configure Replication | Patrick Lim | To Do |  | 3 | 3 | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; SMG; SQL; SSL; SSRS
Task |  |  |  | Set Up Domain and Insight Logins | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
Task |  |  |  | Configure Maintenance Plan | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
Task |  |  |  | Configure Kerberos for Data Services | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
Task |  |  |  | Update Data Paths | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
Task |  |  |  | SMG Install RDL Files for Reporting | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | PBI; SMG; SQL; SSRS
Task |  |  |  | Install Analysis Server | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL
Task |  |  |  | Configure Agent Jobs | Patrick Lim | To Do |  | 1 |  | \DevOps\data.srvcs | \RCM Services\2020\20Q3\20Q308\163 | SMG; SQL

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | Select User... | Done | Approved | Select User... | Active | Select User... | Committed | Select User... | Done | Select User... | Done | Select User... | Closed | Select User... | Approved | Select User... | Done | Select User... | Closed | Bug | Select User... | Approved | Approved | Done
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \DevOps | \RCM Product | Abdul Mohammed | Abdul Mohammed | In Progress | Committed | Abdul Mohammed | Approved | Abdul Mohammed | Design | Abdul Mohammed | In Progress | Abdul Mohammed | In Progress | Abdul Mohammed | Open | Abdul Mohammed | Committed | Abdul Mohammed | In Progress | Abdul Mohammed | Design | Case | Abdul Mohammed | Committed | Committed | In Progress
|  |  |  | \DevOps\app.srvcs | \RCM Product\2019 | Adam Craft | Adam Craft | New | Done | Adam Craft | Closed | Adam Craft | Done | Adam Craft | New | Adam Craft | New | Adam Craft | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Impediment_System.State | Adam Craft | Done | Adam Craft | Removed | Adam Craft | Ready | Change Request | Adam Craft | Done | Done | Removed
|  |  |  | \DevOps\core.srvcs | \RCM Product\2019\19Q1 | Adam Nausley | Adam Nausley | Removed | New | Adam Nausley | Committed | Adam Nausley | In Progress | Adam Nausley | Removed | Adam Nausley | Removed | Adam Nausley |  | Adam Nausley | New | Adam Nausley | To Do | Adam Nausley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Test Case_System.State | Epic | Adam Nausley | New | New | To Do
|  |  |  | \DevOps\data.srvcs | \RCM Product\2019\19Q1\19Q1 M1 | Adam Thornsley | Adam Thornsley | VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_3E-A0-10-AD-B5-8B-29-2F-67-37-CE-1A-7B-2E-07-D7-3C-72-25-0F | Removed | Adam Thornsley | Completed | Adam Thornsley | New | Adam Thornsley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Epic_System.State | Adam Thornsley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Feature_System.State | Adam Thornsley |  | Adam Thornsley | Removed | Adam Thornsley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Task_System.State | Adam Thornsley |  | Feature | Adam Thornsley | Removed | Removed | VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_7A-3C-61-24-4A-C7-A0-9F-0C-58-9B-DC-C1-AC-0D-E9-6C-AB-66-4C
|  |  |  | \DevOps\identity.srvcs | \RCM Product\2019\19Q1\19Q1 M2 | Andy Pardue | Andy Pardue |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Bug_System.State | Andy Pardue | Design | Andy Pardue | To Do | Andy Pardue |  | Andy Pardue |  | Andy Pardue |  | Andy Pardue | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Product Backlog Item_System.State | Andy Pardue |  | Andy Pardue |  | Impediment | Andy Pardue | Active | VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_FC-70-5F-3C-24-90-2F-CA-47-22-34-91-99-86-B3-1A-2D-B3-FF-2F
|  |  |  | \DevOps\tenant.srvcs | \RCM Product\2019\19Q1\19Q1 M3 | Anthony Rogers | Anthony Rogers |  |  | Anthony Rogers | Done | Anthony Rogers | Validation | Anthony Rogers |  | Anthony Rogers |  | Anthony Rogers |  | Anthony Rogers |  | Anthony Rogers |  | Anthony Rogers |  | Product Backlog Item | Anthony Rogers | Closed
|  |  |  | \DevOps\vendor.srvcs | \RCM Product\2019\19Q2 | Benjamin Cradick | Benjamin Cradick |  |  | Benjamin Cradick | In Planning | Benjamin Cradick | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Change Request_System.State | Benjamin Cradick |  | Benjamin Cradick |  | Benjamin Cradick |  | Benjamin Cradick |  | Benjamin Cradick |  | Benjamin Cradick |  | Task | Benjamin Cradick | Completed
|  |  |  | \DevOps\web.srvcs | \RCM Product\2019\19Q2\19Q2 M1 | Bobbi Lilly-Trakas | Bobbi Lilly-Trakas |  |  | Bobbi Lilly-Trakas | In Progress | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Bobbi Lilly-Trakas |  | Test Case | Bobbi Lilly-Trakas | Design
|  |  |  | \RCM Product | \RCM Product\2019\19Q2\19Q2 M2 | Brent Freeman | Brent Freeman |  |  | Brent Freeman | New | Brent Freeman |  | Brent Freeman |  | Brent Freeman |  | Brent Freeman |  | Brent Freeman |  | Brent Freeman |  | Brent Freeman |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_System.WorkItemType | Brent Freeman | In Planning
|  |  |  | \RCM Product\RCM Cloud | \RCM Product\2019\19Q2\19Q2 M3 | Brian Freed | Brian Freed |  |  | Brian Freed | Not in Progress | Brian Freed |  | Brian Freed |  | Brian Freed |  | Brian Freed |  | Brian Freed |  | Brian Freed |  | Brian Freed |  |  | Brian Freed | In Progress
|  |  |  | \RCM Product\RCM PM | \RCM Product\2019\19Q3 | Brian Stockell | Brian Stockell |  |  | Brian Stockell | Open | Brian Stockell |  | Brian Stockell |  | Brian Stockell |  | Brian Stockell |  | Brian Stockell |  | Brian Stockell |  | Brian Stockell |  |  | Brian Stockell | Not in Progress
|  |  |  | \Services | \RCM Product\2019\19Q3\19Q3 M1 | Charles Musgrave | Charles Musgrave |  |  | Charles Musgrave | Pending | Charles Musgrave |  | Charles Musgrave |  | Charles Musgrave |  | Charles Musgrave |  | Charles Musgrave |  | Charles Musgrave |  | Charles Musgrave |  |  | Charles Musgrave | Open
|  |  |  | \Services\IMP | \RCM Product\2019\19Q3\19Q3 M2 | Charles Record | Charles Record |  |  | Charles Record | Ready | Charles Record |  | Charles Record |  | Charles Record |  | Charles Record |  | Charles Record |  | Charles Record |  | Charles Record |  |  | Charles Record | Pending
|  |  |  | \Services\IMP\Case | \RCM Product\2019\19Q3\19Q3 M3 | Chris Padilla | Chris Padilla |  |  | Chris Padilla | Removed | Chris Padilla |  | Chris Padilla |  | Chris Padilla |  | Chris Padilla |  | Chris Padilla |  | Chris Padilla |  | Chris Padilla |  |  | Chris Padilla | Ready
|  |  |  | \Services\PRO | \RCM Product\2019\19Q4 | Daniel Conoyer | Daniel Conoyer |  |  | Daniel Conoyer | To Do | Daniel Conoyer |  | Daniel Conoyer |  | Daniel Conoyer |  | Daniel Conoyer |  | Daniel Conoyer |  | Daniel Conoyer |  | Daniel Conoyer |  |  | Daniel Conoyer | To Do
|  |  |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_System.AreaPath | \RCM Product\2020 | Darrell Berridge | Darrell Berridge |  |  | Darrell Berridge | Validation | Darrell Berridge |  | Darrell Berridge |  | Darrell Berridge |  | Darrell Berridge |  | Darrell Berridge |  | Darrell Berridge |  | Darrell Berridge |  |  | Darrell Berridge | Validation
[5 empty] | \RCM Product\2020\20Q1 | Debbie Fridley | Debbie Fridley |  |  | Debbie Fridley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Case_System.State | Debbie Fridley |  | Debbie Fridley |  | Debbie Fridley |  | Debbie Fridley |  | Debbie Fridley |  | Debbie Fridley |  | Debbie Fridley |  |  | Debbie Fridley | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_System.State
[5 empty] | \RCM Product\2020\20Q2 | Derek Veit | Derek Veit |  |  | Derek Veit |  | Derek Veit |  | Derek Veit |  | Derek Veit |  | Derek Veit |  | Derek Veit |  | Derek Veit |  | Derek Veit |  |  | Derek Veit
[5 empty] | \RCM Product\2020\20Q3 | Gustin Hubble | Gustin Hubble |  |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  | Gustin Hubble |  |  | Gustin Hubble
[5 empty] | \RCM Product\2020\20Q4 | Heather Gentile | Heather Gentile |  |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  | Heather Gentile |  |  | Heather Gentile
[5 empty] | \RCM Product\2021 | Jeff Burton | Jeff Burton |  |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  | Jeff Burton |  |  | Jeff Burton
[5 empty] | \RCM Product\2021\21Q1 | Jim Zeroff | Jim Zeroff |  |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  | Jim Zeroff |  |  | Jim Zeroff
[5 empty] | \RCM Product\2021\21Q2 | Jon King | Jon King |  |  | Jon King |  | Jon King |  | Jon King |  | Jon King |  | Jon King |  | Jon King |  | Jon King |  | Jon King |  |  | Jon King
[5 empty] | \RCM Product\2021\21Q3 | Jonathan Pham | Jonathan Pham |  |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  | Jonathan Pham |  |  | Jonathan Pham
[5 empty] | \RCM Product\2021\21Q4 | Josh Price | Josh Price |  |  | Josh Price |  | Josh Price |  | Josh Price |  | Josh Price |  | Josh Price |  | Josh Price |  | Josh Price |  | Josh Price |  |  | Josh Price
[5 empty] | \RCM Services | Justin Coker | Justin Coker |  |  | Justin Coker |  | Justin Coker |  | Justin Coker |  | Justin Coker |  | Justin Coker |  | Justin Coker |  | Justin Coker |  | Justin Coker |  |  | Justin Coker
[5 empty] | \RCM Services\2019 | Kyle Maasen | Kyle Maasen |  |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  | Kyle Maasen |  |  | Kyle Maasen
[5 empty] | \RCM Services\2019\19Q1 | Lauren Lamb | Lauren Lamb |  |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  | Lauren Lamb |  |  | Lauren Lamb
[5 empty] | \RCM Services\2019\19Q1\100 | Lesley Ruby | Lesley Ruby |  |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  | Lesley Ruby |  |  | Lesley Ruby
[5 empty] | \RCM Services\2019\19Q1\101 | Lily S. Chang | Lily S. Chang |  |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  | Lily S. Chang |  |  | Lily S. Chang
[5 empty] | \RCM Services\2019\19Q1\102 | Matt Boswell | Matt Boswell |  |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  | Matt Boswell |  |  | Matt Boswell
[5 empty] | \RCM Services\2019\19Q1\103 | Patrick Lim | Patrick Lim |  |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  | Patrick Lim |  |  | Patrick Lim
[5 empty] | \RCM Services\2019\19Q2 | Phil Couto | Phil Couto |  |  | Phil Couto |  | Phil Couto |  | Phil Couto |  | Phil Couto |  | Phil Couto |  | Phil Couto |  | Phil Couto |  | Phil Couto |  |  | Phil Couto
[5 empty] | \RCM Services\2019\19Q2\104 | Rita Schneider | Rita Schneider |  |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  | Rita Schneider |  |  | Rita Schneider
[5 empty] | \RCM Services\2019\19Q2\105 | Robert Kilian | Robert Kilian |  |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  | Robert Kilian |  |  | Robert Kilian
[5 empty] | \RCM Services\2019\19Q2\106 | Robert Klocke | Robert Klocke |  |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  | Robert Klocke |  |  | Robert Klocke
[5 empty] | \RCM Services\2019\19Q2\107 | Ruth Dyrness | Ruth Dyrness |  |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  | Ruth Dyrness |  |  | Ruth Dyrness
[5 empty] | \RCM Services\2019\19Q3 | Sam Ellison | Sam Ellison |  |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  | Sam Ellison |  |  | Sam Ellison
[5 empty] | \RCM Services\2019\19Q3\108 | Scott Vance | Scott Vance |  |  | Scott Vance |  | Scott Vance |  | Scott Vance |  | Scott Vance |  | Scott Vance |  | Scott Vance |  | Scott Vance |  | Scott Vance |  |  | Scott Vance
[5 empty] | \RCM Services\2019\19Q3\109 | Stephanie Welch | Stephanie Welch |  |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  | Stephanie Welch |  |  | Stephanie Welch
[5 empty] | \RCM Services\2019\19Q3\110 | Terri Kozlowski | Terri Kozlowski |  |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  | Terri Kozlowski |  |  | Terri Kozlowski
[5 empty] | \RCM Services\2019\19Q3\111 | Tina Stocum | Tina Stocum |  |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  | Tina Stocum |  |  | Tina Stocum
[5 empty] | \RCM Services\2019\19Q3\112 | Todd Blum | Todd Blum |  |  | Todd Blum |  | Todd Blum |  | Todd Blum |  | Todd Blum |  | Todd Blum |  | Todd Blum |  | Todd Blum |  | Todd Blum |  |  | Todd Blum
[5 empty] | \RCM Services\2019\19Q3\113 | Tom Arnold | Tom Arnold |  |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  | Tom Arnold |  |  | Tom Arnold
[5 empty] | \RCM Services\2019\19Q3\114 | Tom Latzo | Tom Latzo |  |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  | Tom Latzo |  |  | Tom Latzo
[5 empty] | \RCM Services\2019\19Q3\115 | Trish Harmon | Trish Harmon |  |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  | Trish Harmon |  |  | Trish Harmon
[5 empty] | \RCM Services\2019\19Q4 | Valerie Langdon | Valerie Langdon |  |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  | Valerie Langdon |  |  | Valerie Langdon
[5 empty] | \RCM Services\2019\19Q4\116 | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Bug_System.AssignedTo | VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_64-CE-8C-F6-7E-FB-2A-9B-A5-68-8E-DB-7A-82-83-6E-40-6B-AD-A4 |  |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Case_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Change Request_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Epic_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Feature_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Impediment_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Product Backlog Item_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Task_System.AssignedTo |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_Test Case_System.AssignedTo |  |  | all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_System.AssignedTo
\RCM Services\2019\19Q4\117
\RCM Services\2019\19Q4\118
\RCM Services\2019\19Q4\119
\RCM Services\2019\19Q4\120
\RCM Services\2019\19Q4\121
\RCM Services\2019\19Q4\122
\RCM Services\2019\19Q4\123
\RCM Services\2019\19Q4\124
\RCM Services\2019\19Q4\125
\RCM Services\2019\19Q4\126
\RCM Services\2019\19Q4\127
\RCM Services\2019\19Q4\128
\RCM Services\2019\19Q4\129
\RCM Services\2020
\RCM Services\2020\20Q1
\RCM Services\2020\20Q1\130
\RCM Services\2020\20Q1\131
\RCM Services\2020\20Q1\132
\RCM Services\2020\20Q1\133
\RCM Services\2020\20Q1\134
\RCM Services\2020\20Q1\135
\RCM Services\2020\20Q1\136
\RCM Services\2020\20Q1\137
\RCM Services\2020\20Q1\138
\RCM Services\2020\20Q1\139
\RCM Services\2020\20Q1\140
\RCM Services\2020\20Q1\141
\RCM Services\2020\20Q2
\RCM Services\2020\20Q2\142
\RCM Services\2020\20Q2\143
\RCM Services\2020\20Q2\144
\RCM Services\2020\20Q2\145
\RCM Services\2020\20Q2\146
\RCM Services\2020\20Q2\147
\RCM Services\2020\20Q2\148
\RCM Services\2020\20Q2\149
\RCM Services\2020\20Q2\150
\RCM Services\2020\20Q2\151
\RCM Services\2020\20Q2\152
\RCM Services\2020\20Q2\153
\RCM Services\2020\20Q2\154
\RCM Services\2020\20Q3
\RCM Services\2020\20Q3\20Q307
\RCM Services\2020\20Q3\20Q307\155
\RCM Services\2020\20Q3\20Q307\156
\RCM Services\2020\20Q3\20Q307\157
\RCM Services\2020\20Q3\20Q307\158
\RCM Services\2020\20Q3\20Q308
\RCM Services\2020\20Q3\20Q308\159
\RCM Services\2020\20Q3\20Q308\160
\RCM Services\2020\20Q3\20Q308\161
\RCM Services\2020\20Q3\20Q308\162
\RCM Services\2020\20Q3\20Q308\163
\RCM Services\2020\20Q3\20Q309
\RCM Services\2020\20Q3\20Q309\164
\RCM Services\2020\20Q3\20Q309\165
\RCM Services\2020\20Q3\20Q309\166
\RCM Services\2020\20Q3\20Q309\167
\RCM Services\2020\20Q4
\RCM Services\2020\20Q4\20Q410
\RCM Services\2020\20Q4\20Q410\168
\RCM Services\DevOps
\RCM Services\DevOps\2018
\RCM Services\DevOps\2018\RCM Sprint 1
\RCM Services\DevOps\2018\RCM Sprint 2
\RCM Services\DevOps\2018\RCM Sprint 3
\RCM Services\DevOps\2018\RCM Sprint 4
\RCM Services\DevOps\2018\RCM Sprint 5
\RCM Services\DevOps\2018\RCM Sprint 6
\RCM Services\DevOps\2018\RCM Sprint 7
\RCM Services\DevOps\2018\RCM Sprint 8
\RCM Services\DevOps\2018\RCM Sprint 9
all_VSTS_95b300b4_b3d3_49c7_9573_c597ea7be519_System.IterationPath